## All Tasks
Task | Category | Criticality | Time Est. | Status | Assignee | Notes
Delete Canva template slides 19-31 (Once other slides are complete) | Presentation | 🔴 CRITICAL | 5 min | Complete | Nikita
Build Data Integration Findings slide (Prince Hall + Amerihost) | Presentation | 🔴 CRITICAL | 20 min | Complete | Khaled
Add a slide about the funding paradox to new presentation - slide 12 from prior | Presentation | 🔴 CRITICAL | 20 min | Complete | Khaled
Insert Tableau vizzes into slides 7, 12, 20 | Presentation | 🔴 CRITICAL | 20 min
Fix GitHub link in website nav (currently placeholder) | Website | 🔴 CRITICAL | 5 min | Complete | Andy
Rename "Taxpayer Protection Score (TPS)" → "Audit Health Score" in glossary | Website | 🔴 CRITICAL | 10 min | Complete | Andy
Add repo description + website URL in GitHub About section | GitHub | 🔴 CRITICAL | 5 min | In Progress | Khaled & Andy
Fix Slide 5 (Solution) — add website name + screenshot | Presentation | 🟠 HIGH | 15 min | Complete | Nikita
Add website link to conclusion slide | Presentation | 🟠 HIGH | 2 min | Complete | Nikita
Fix Slide 12 (Data Viz) — add key insights/stats | Presentation | 🟠 HIGH | 20 min |  | Nikita
Fix Slide 16 (User Stories) — replace placeholder content | Presentation | 🟠 HIGH | 25 min | Complete | Nikita
Polish Slide 18 (Conclusion) — strong closing statement | Presentation | 🟠 HIGH | 15 min | Complete | Nikita
Rename TPS → Audit Health Score throughout all slides | Presentation | 🟠 HIGH | 15 min | Complete | Khaled
Fill Website Placeholder B with Card B vizzes (Funding Over Time) | Website | 🟠 HIGH | 45 min | Complete | Andy
Fill Website Placeholder D + fix duplicate label | Website | 🟠 HIGH | 45 min | Complete | Andy
Add GitHub topics/tags (datathon, federal-spending, audit, tableau, alteryx) | GitHub | 🟠 HIGH | 5 min | In Progress | Khaled & Andy
Make GitHub repo public (if judges need access) | GitHub | 🟠 HIGH | 2 min | In Progress | Khaled & Andy
Merge or close GitHub PR #1 (feature/dashboard) | GitHub | 🟠 HIGH | 10 min | In Progress | Khaled & Andy
Add appendix slide | Presentation | 🟠 HIGH | 10 min | Complete | Mariam
Add screenshots to slides 8, 9, 10 (Glossary, Dataset Guide, Use Cases) | Presentation | 🟡 MEDIUM | 20 min
Review Slide 13 (Case Studies/ML) for accuracy | Presentation | 🟡 MEDIUM | 10 min
Fix Slide 17 icons (note says "change icons") | Presentation | 🟡 MEDIUM | 10 min | Complete | Nikita
Add Case Studies section to website | Website | 🟡 MEDIUM | 90 min | Complete | Andy
Add Audit Health Score explainer page to website | Website | 🟡 MEDIUM | 60 min | Complete | Andy
Card A - adjust the first visual to be the top 10 states (50.9%) | Website | 🟡 MEDIUM | 20 min | Complete | Andy
Add glossary button to homepage | Website | 🟡 MEDIUM | 20 min | Complete | Andy
Duplicate navigator button below tableau visualizations & add a step to tour | Website | 🟡 MEDIUM | 20 min | Complete | Andy
Delete dead GitHub branches (docs/report-and-slides, feature/modeling-forecast) | GitHub | 🟡 MEDIUM | 5 min | Complete | Andy
Take Alteryx workflow screenshots (3-4 key workflows) | GitHub | 🟡 MEDIUM | 30 min | In Progress | Khaled & Andy
Take Tableau viz screenshots for GitHub (Card A, B, C) | GitHub | 🟡 MEDIUM | 20 min | In Progress | Khaled & Andy
Create data pipeline diagram (USAspending → FAC → SAM flow) | GitHub | 🟡 MEDIUM | 25 min | In Progress | Khaled & Andy
Create Audit Health Score tier visual for GitHub | GitHub | 🟡 MEDIUM | 15 min | In Progress | Khaled & Andy
Upload all visual assets to GitHub assets/ folder | GitHub | 🟡 MEDIUM | 10 min | In Progress | Khaled & Andy
Add Key Findings section to GitHub README | GitHub | 🟡 MEDIUM | 20 min | In Progress | Khaled & Andy
Add Alteryx pipeline section to GitHub README with screenshots | GitHub | 🟡 MEDIUM | 15 min | In Progress | Khaled & Andy
Add Tableau visualizations section to GitHub README | GitHub | 🟡 MEDIUM | 15 min | In Progress | Khaled & Andy
Add Audit Health Score methodology section to GitHub README | GitHub | 🟡 MEDIUM | 15 min | In Progress | Khaled & Andy
Add Case Studies preview to GitHub README | GitHub | 🟡 MEDIUM | 15 min | In Progress | Khaled & Andy
Add slide numbers to presentation | Presentation | 🟢 LOW | 5 min
Add speaker notes to key slides | Presentation | 🟢 LOW | 30 min
Final typo/grammar check on slides | Presentation | 🟢 LOW | 15 min
Test presentation mode | Presentation | 🟢 LOW | 10 min
Export final presentation PDF/PPT | Presentation | 🟢 LOW | 5 min
Ensure all slide fonts consistent | Presentation | 🟢 LOW | 10 min
Ensure all slide colors consistent | Presentation | 🟢 LOW | 10 min
Add hero banner/logo to GitHub README | GitHub | 🟢 LOW | 15 min | In Progress | Khaled & Andy
Verify all GitHub README links work | GitHub | 🟢 LOW | 10 min | In Progress | Khaled & Andy
Protect GitHub main branch | GitHub | 🟢 LOW | 3 min | In Progress | Khaled & Andy
Add final presentation PDF/PPT to GitHub repo | GitHub | 🟢 LOW | 5 min | In Progress | Khaled & Andy
Final deck review — flow and narrative | Presentation | 🟢 LOW | 30 min
Add GitHub badges (build status, license) | GitHub | ⚪ OPTIONAL | 10 min
Create CONTRIBUTING.md for GitHub | GitHub | ⚪ OPTIONAL | 15 min
Test GitHub repo from fresh browser (judge perspective) | GitHub | ⚪ OPTIONAL | 10 min
Review website from fresh browser (judge perspective) | Website | ⚪ OPTIONAL | 10 min
Available after deadline
Replace first guided questions in Next Steps with "Which Federal Agencies are distributing the most funding?" | Website | 🟠 HIGH |  |  | Andy
Sticky header menu | Website | 🟡 MEDIUM | 20 min | In Progress | Andy
Update embed for Map – Federal Grant Spending by State | Website | 🟡 MEDIUM | 20 min | In Progress | Andy
Test all Tableau embeds on website | Website | 🟡 MEDIUM | 20 min | In Progress | Khaled
Website final QA — all links, typos | Website | 🟢 LOW | 30 min
Add website favicon | Website | ⚪ OPTIONAL | 10 min
Website name - check with Pranavi where she wanted this located

## By Category
PRESENTATION TASKS
# | Task | Criticality | Time Est. | Status
1 | Delete Canva template slides 19-31 | 🔴 CRITICAL | 5 min
2 | Build Data Integration Findings slide (Prince Hall + Amerihost) | 🔴 CRITICAL | 45 min
3 | Insert Tableau vizzes into slides 7, 12, 20 | 🔴 CRITICAL | 20 min
4 | Add 2-3 Audit Health Score examples to slides | 🔴 CRITICAL | 30 min
8 | Fix Slide 5 (Solution) — add website name + screenshot | 🟠 HIGH | 15 min
9 | Fix Slide 12 (Data Viz) — add key insights/stats | 🟠 HIGH | 20 min
10 | Fix Slide 16 (User Stories) — replace placeholder content | 🟠 HIGH | 25 min
11 | Polish Slide 18 (Conclusion) — strong closing statement | 🟠 HIGH | 15 min
12 | Rename TPS → Audit Health Score throughout all slides | 🟠 HIGH | 15 min
18 | Add screenshots to slides 8, 9, 10 (Glossary, Dataset Guide, Use Cases) | 🟡 MEDIUM | 20 min
19 | Fix Slide 17 icons (note says "change icons") | 🟡 MEDIUM | 10 min
20 | Ensure all slide fonts consistent | 🟡 MEDIUM | 10 min
21 | Ensure all slide colors consistent | 🟡 MEDIUM | 10 min
22 | Review Slide 13 (Case Studies/ML) for accuracy | 🟡 MEDIUM | 10 min
37 | Add slide numbers to presentation | 🟢 LOW | 5 min
38 | Add speaker notes to key slides | 🟢 LOW | 30 min
39 | Final typo/grammar check on slides | 🟢 LOW | 15 min
40 | Test presentation mode | 🟢 LOW | 10 min
41 | Export final presentation PDF | 🟢 LOW | 5 min
48 | Final deck review — flow and narrative | 🟢 LOW | 30 min
WEBSITE TASKS
# | Task | Criticality | Time Est. | Status
5 | Fix GitHub link in website nav (currently placeholder) | 🔴 CRITICAL | 5 min
6 | Rename "Taxpayer Protection Score (TPS)" → "Audit Health Score" in glossary | 🔴 CRITICAL | 10 min
13 | Fill Website Placeholder B with Card B vizzes (Funding Over Time) | 🟠 HIGH | 45 min
14 | Fill Website Placeholder D + fix duplicate label | 🟠 HIGH | 45 min
23 | Add Case Studies section to website | 🟡 MEDIUM | 90 min
24 | Add Audit Health Score explainer page to website | 🟡 MEDIUM | 60 min
25 | Test all Tableau embeds on website | 🟡 MEDIUM | 20 min
42 | Mobile responsiveness check on website | 🟢 LOW | 20 min
43 | Website final QA — all links, typos | 🟢 LOW | 30 min
49 | Add website favicon | ⚪ OPTIONAL | 10 min
50 | Add analytics tracking to website | ⚪ OPTIONAL | 15 min
54 | Review website from fresh browser (judge perspective) | ⚪ OPTIONAL | 10 min
GITHUB TASKS
# | Task | Criticality | Time Est. | Status
7 | Add repo description + website URL in GitHub About section | 🔴 CRITICAL | 5 min
15 | Add GitHub topics/tags (datathon, federal-spending, audit, tableau, alteryx) | 🟠 HIGH | 5 min
16 | Make GitHub repo public (if judges need access) | 🟠 HIGH | 2 min
17 | Merge or close GitHub PR #1 (feature/dashboard) | 🟠 HIGH | 10 min
26 | Delete dead GitHub branches (docs/report-and-slides, feature/modeling-forecast) | 🟡 MEDIUM | 5 min
27 | Take Alteryx workflow screenshots (3-4 key workflows) | 🟡 MEDIUM | 30 min
28 | Take Tableau viz screenshots for GitHub (Card A, B, C) | 🟡 MEDIUM | 20 min
29 | Create data pipeline diagram (USAspending → FAC → SAM flow) | 🟡 MEDIUM | 25 min
30 | Create Audit Health Score tier visual for GitHub | 🟡 MEDIUM | 15 min
31 | Upload all visual assets to GitHub assets/ folder | 🟡 MEDIUM | 10 min
32 | Add Key Findings section to GitHub README | 🟡 MEDIUM | 20 min
33 | Add Alteryx pipeline section to GitHub README with screenshots | 🟡 MEDIUM | 15 min
34 | Add Tableau visualizations section to GitHub README | 🟡 MEDIUM | 15 min
35 | Add Audit Health Score methodology section to GitHub README | 🟡 MEDIUM | 15 min
36 | Add Case Studies preview to GitHub README | 🟡 MEDIUM | 15 min
44 | Add hero banner/logo to GitHub README | 🟢 LOW | 15 min
45 | Verify all GitHub README links work | 🟢 LOW | 10 min
46 | Protect GitHub main branch | 🟢 LOW | 3 min
47 | Add final presentation PDF to GitHub repo | 🟢 LOW | 5 min
51 | Add GitHub badges (build status, license) | ⚪ OPTIONAL | 10 min
52 | Create CONTRIBUTING.md for GitHub | ⚪ OPTIONAL | 15 min
53 | Test GitHub repo from fresh browser (judge perspective) | ⚪ OPTIONAL | 10 min

## Summary
AGA DATATHON 2026 - TASK SUMMARY
BY CRITICALITY
Criticality | Tasks | Est. Time
🔴 CRITICAL | 7 | ~2 hrs
🟠 HIGH | 10 | ~3.3 hrs
🟡 MEDIUM | 19 | ~6.3 hrs
🟢 LOW | 12 | ~3 hrs
⚪ OPTIONAL | 6 | ~1.1 hrs
TOTAL | 54 | ~15.7 hrs
BY CATEGORY
Category | Tasks | Est. Time
Presentation | 20 | ~5 hrs 45 min
Website | 12 | ~6 hrs
GitHub | 22 | ~4 hrs 35 min
TOTAL | 54 | ~15.7 hrs
DEADLINE QUICK REFERENCE
Time Available | Focus On
2 hours | All 🔴 Critical (7 tasks)
4 hours | All 🔴 + 🟠 High (17 tasks)
6 hours | All 🔴 + 🟠 + Presentation/Website 🟡 Medium
8+ hours | Everything through 🟢 Low

## Minimum Viable
MINIMUM VIABLE SUBMISSION
Complete these 7 items for a competitive submission:
# | Task | Category | Time | Status
1 | Delete slides 19-31 | Presentation | 5 min
2 | Build Data Integration Findings slide | Presentation | 45 min
3 | Insert Tableau vizzes into slides | Presentation | 20 min
4 | Audit Health Score examples | Presentation | 30 min
5 | Fix website GitHub link | Website | 5 min
6 | Rename TPS → Audit Health Score (glossary) | Website | 10 min
7 | GitHub About section | GitHub | 5 min
|  | TOTAL: | ~2 hours